## Sheet1
72 hours | Description | User Story | PBI Number | Task | Task time | Scrum meeting dates
-3 Hours = 69 hours | SPRINT meetings |  | NA |  |  | Tuesdays 6 PM
-2 Hours = 67 hours | Design |  | NA |  |  | Friday 6 PM
-2 Hours = 65 hours | BUGFIX PBI: .csv file handling | As an election official, I want the voting system to | 1 | System test writing and testing | 20 minutes | Saturday 5 PM
|  | be able to take in an.csv files so I don’t have to |  | Unit test writing and testing | 20 minutes
|  | manually type information in. |  | Integration test writing and testing | 20 minutes
|  |  |  | Test log writing | 30 minutes
|  |  |  | Coding | 30 minutes
-6 Hours = 59 hours | BUGFIX PBI: tiebreaker functionality | As an election official, I want a tiebreaker for CPL | 2 | Coding | 5 hrs
|  | that works so that we can hold fair and honest elections. |  | testing | 1 hr
-12 Hours = 47 Hours | PBI: CPL Multiple files | As an election official, I want the voting system to | 3 | CMD asks for more files coding | 1 hour
|  | be able to also accept multiple CPL files and |  | refactor voting algorithm to take in multiple CPL files | 3 hours
|  | produce the correct result corresponding with |  | System test writing and testing | 2 hours
|  | those files |  | Unit test writing and testing | 2 hours
|  |  |  | Integration test writing and testing | 2 hours
|  |  |  | JavaDocs Documentation | 30 minutes
|  |  |  | Test file creation | 30 minutes
|  |  |  | Code documentation | 30 minutes
|  |  |  | Test log writing | 30 minutes
-4 Hours = 43 Hours | PBI: OPL Multiple Files | As an election official, I want the voting system to | 4 | CMD asks for more files | 30 minutes
|  | be able to also accept OPL files and produce the |  | refactor voting algorithm to take in multiple OPL files | 30 minutes
|  | correct result corresponding with those files |  | System test writing and testing | 30 minutes
|  |  |  | Unit test writing and testing | 30 minutes
|  |  |  | Integration test writing and testing | 30 minutes
|  |  |  | JavaDocs Documentation | 15 minutes
|  |  |  | Test file creation | 30 minutes
|  |  |  | Code documentation | 15 minutes
|  |  |  | Test log writing | 30 minutes
-4 Hours = 39 Hours | PBI: MPO Files in general | As an election official, I want the voting system to be | 5 | Refactor CMD to take in MPO file | 30 minutes
|  | able to also accept an MPO file and produce the correct |  | System test writing and testing | 30 minutes
|  | result corresponding with that file |  | Unit test writing and testing | 30 minutes
|  |  |  | Integration test writing and testing | 30 minutes
|  |  |  | JavaDocs Documentation | 30 minutes
|  |  |  | Test file creation | 15 minutes
|  |  |  | Code documentation | 30 minutes
|  |  |  | Test log writing | 15 minutes
30 minutes
-4 Hours = 35 Hours | PBI: MPO Multiple files | As an election official, I want the voting system to | 6 | CMD asks for more MPO files coding | 30 minutes
|  | be able to also accept multiple MPO files and |  | System test writing and testing | 30 minutes
|  | produce the correct result corresponding with |  | Unit test writing and testing | 30 minutes
|  | those files |  | Integration test writing and testing | 30 minutes
|  |  |  | JavaDocs Documentation | 30 minutes
|  |  |  | Test file creation | 15 minutes
|  |  |  | Code documentation | 30 minutes
|  |  |  | Test log writing | 15 minutes
|  |  |  | refactor voting algorithm to take in multiple MPO files | 30 minutes
-5 Hours = 23 Hours | PBI: MPO Election | As an election official, I want the voting system | 7 | refactor voting algorithm to support MPO election type | 1 hour
|  | to be able to also handle MPO election types |  | System test writing and testing | 45 minutes
|  |  |  | Unit test writing and testing | 1 hour
|  |  |  | Integration test writing and testing | 30 minutes
|  |  |  | JavaDocs Documentation | 15 minutes
|  |  |  | Test file creation | 45 minutes
|  |  |  | Code documentation | 15 minutes
|  |  |  | Test log writing | 30 minutes
-4 Hours = 19 Hours | PBI: MV Files in general | As an election official, I want the voting system | 8 | Refactor CMD to take in MV file | 45 minutes
|  | to be able to also handle MPO election types |  | System test writing and testing | 30 minutes
|  |  |  | Unit test writing and testing | 30 minutes
|  |  |  | Integration test writing and testing | 30 minutes
|  |  |  | JavaDocs Documentation | 15 minutes
|  |  |  | Test file creation | 45 minutes
|  |  |  | Code documentation | 15 minutes
|  |  |  | Test log writing | 30 minutes
-4.25 Hours = 14.75 Hours | PBI: MV Multiple Files | As an election official, I want the voting system to be able to also accept multiple MV files and produce the correct result corresponding with those files | 9 | CMD asks for more MV files coding | 45 minutes
|  | to be able to also accept multiple MV files and produce |  | System test writing and testing | 30 minutes
|  | the correct result corresponding with those files |  | Unit test writing and testing | 30 minutes
|  |  |  | Integration test writing and testing | 30 minutes
|  |  |  | JavaDocs Documentation | 15 minutes
|  |  |  | Test file creation | 45 minutes
|  |  |  | Code documentation | 15 minutes
|  |  |  | Test log writing | 30 minutes
|  |  |  | refactor voting algorithm to take in multiple MV files | 15 minutes